# SAFe SDLC Process

The Scaled Agile Framework (SAFe) is a widely recognized and adopted set of organization and workflow patterns designed to guide enterprises in scaling lean and agile practices effectively. This Software Development Life Cycle (SDLC) process leverages the principles and practices of SAFe to provide a structured and comprehensive framework for developing and delivering software products at the enterprise level. By implementing this SAFe-based SDLC, organizations can ensure enhanced alignment by establishing a common vision and priorities across all teams, improved collaboration through standardized processes and communication channels, and consistent value delivery by focusing on delivering incremental value to customers throughout the development lifecycle. SAFe's principles of alignment, built-in quality, transparency, and decentralized decision-making are crucial for the success of enterprise-level software development, enabling organizations to respond quickly to changing market demands, reduce time to market, and improve the quality of their products.

Industry / Domain: Software Development

Version: 1.0

Generated On: 2026-01-19 15:45:36

# Document Control

| Version | Date | Author | Description |
| --- | --- | --- | --- |
| 1.0 | 2026-01-19 | Process Architect | Initial generated process specification |

# Table of Contents

Right-click and select 'Update Field' to generate the Table of Contents.

# 1.0 Process Overview

The Scaled Agile Framework (SAFe) is a widely recognized and adopted set of organization and workflow patterns designed to guide enterprises in scaling lean and agile practices effectively. This Software Development Life Cycle (SDLC) process leverages the principles and practices of SAFe to provide a structured and comprehensive framework for developing and delivering software products at the enterprise level. By implementing this SAFe-based SDLC, organizations can ensure enhanced alignment by establishing a common vision and priorities across all teams, improved collaboration through standardized processes and communication channels, and consistent value delivery by focusing on delivering incremental value to customers throughout the development lifecycle. SAFe's principles of alignment, built-in quality, transparency, and decentralized decision-making are crucial for the success of enterprise-level software development, enabling organizations to respond quickly to changing market demands, reduce time to market, and improve the quality of their products.

## 1.1 Assumptions

Teams are trained in SAFe principles

Stakeholders are engaged and supportive

Infrastructure is adequate for CI/CD

There is clear alignment between business and development

## 1.2 Constraints

Budget limitations

Regulatory compliance (e.g., HIPAA, GDPR)

Limited resources (e.g., personnel, infrastructure)

## 1.3 Purpose

This process aims to provide a structured framework for developing and delivering software products at the enterprise level, aligning with strategic business goals and delivering value to stakeholders through Agile and SAFe methodologies. It ensures that software development efforts are aligned with business objectives by prioritizing features that directly contribute to key performance indicators (KPIs) such as increased revenue, reduced costs, or improved customer satisfaction. For example, a key performance indicator (KPI) directly impacted by this process could be a reduction in time-to-market for new features, an increase in customer satisfaction scores, or a decrease in development costs. The process promotes collaboration and communication across teams through standardized processes and regular synchronization meetings, and enables the delivery of high-quality software products in a timely and efficient manner by leveraging continuous integration and continuous delivery (CI/CD) practices.

## 1.4 Scope

This process encompasses all software development activities from initial planning and requirements gathering to production deployment and ongoing maintenance. It includes program management, release train coordination, team-level execution, and applies to large-scale enterprise projects that require cross-team coordination and alignment with strategic business goals. For example, this process would be used for developing a new e-commerce platform, migrating a legacy system to the cloud, or building a new customer relationship management (CRM) platform. This process excludes small, isolated projects that do not require significant cross-team coordination or alignment with enterprise-level objectives, such as developing a simple mobile app, creating a single landing page, or developing a proof-of-concept application.

## 1.5 Industry Sector

Software Development

# 2.0 Stakeholders and Responsibilities

The following is a list of key stakeholders involved in this process. Understanding their roles and responsibilities is crucial for successful implementation.

| Stakeholder | Responsibilities |
| --- | --- |
| Program Manager | Program vision and roadmap Budget and resource allocation Stakeholder management Risk and dependency management |
| Release Train Engineer (RTE) | ART facilitation Program execution Impediment removal SAFe adoption |
| System Architect | Architectural runway Technical guidance System design |
| Development Teams | Feature development Testing Iteration planning |
| Product Management | Program backlog Prioritization Feature definition |
| System Team | Build and test automation Environment provisioning DevOps support |
| Business Owners | Provide business context Validate value delivery Participate in PI Planning |

# 3.0 Process Workflow

The following is a list of key steps in the process workflow.

## 3.1 Pre-PI Planning

Description:

During Pre-PI Planning, the program vision is refined, and the program backlog is prepared to ensure alignment with strategic objectives and market demands. This involves identifying and prioritizing features, defining acceptance criteria, and estimating the effort required for each feature. The outputs of this step include a refined program backlog and a vision document that provides a clear understanding of the program's goals and objectives.

Responsible Parties:

Product Management

Inputs:

Business strategy

Market analysis

Outputs:

Refined program backlog

PI Planning inputs

Success Criteria:

Program backlog is prioritized and ready for PI Planning.

### Required Sub Process(es) for the Step "Pre-PI Planning"

The following details the subprocess flows for the step "Pre-PI Planning".

#### Pre-PI Planning – Analyze Business Strategy

Description:

The Product Management team analyzes the current business strategy to identify key objectives and priorities for the upcoming Program Increment (PI). This involves reviewing market trends, customer feedback, and competitive analysis to ensure that the program backlog aligns with the overall business direction. The team also assesses any new business opportunities or regulatory requirements that may impact the program backlog.

Responsible Party:

Product Management

Inputs:

Business strategy

Market analysis

Outputs:

Business strategy summary

Market analysis summary

Estimated Duration:

2 days

Dependencies:

Success Criteria:

Business strategy is clearly understood

Market analysis is completed

Purpose:

To ensure alignment with business objectives.

Scope:

Analysis of business strategy and market trends.

Process Owner:

Product Manager

Triggers:

New business strategy

Market change

End Conditions:

Business strategy summary completed

Market analysis summary completed

Step Risks and Controls:

Risk: Misinterpretation of business strategy

Control: Regular meetings with business stakeholders

Governance Requirements:

Stakeholder review of business strategy summary

Change Management:

Change Request Process: Formal change request

Versioning Rules: Document versioning

Continuous Improvement:

Review Frequency: Monthly

Improvement Inputs:

Feedback from stakeholders

#### Pre-PI Planning – Refine Program Vision

Description:

Based on the business strategy analysis, the Product Management team refines the program vision to articulate the desired future state of the product. This involves defining the key themes and objectives for the upcoming PI, ensuring that they align with the overall business goals. The team also identifies any potential risks or dependencies that may impact the program vision.

Responsible Party:

Product Management

Inputs:

Business strategy summary

Market analysis summary

Outputs:

Refined program vision

Key themes and objectives

Estimated Duration:

1 day

Dependencies:

Analyze Business Strategy

Success Criteria:

Program vision is clearly defined

Key themes and objectives are identified

Purpose:

To articulate the desired future state of the product.

Scope:

Refinement of program vision and identification of key themes.

Process Owner:

Product Manager

Triggers:

Business strategy summary completed

Market analysis summary completed

End Conditions:

Refined program vision completed

Key themes and objectives completed

Step Risks and Controls:

Risk: Unclear program vision

Control: Regular communication with stakeholders

Governance Requirements:

Stakeholder review of program vision

Change Management:

Change Request Process: Formal change request

Versioning Rules: Document versioning

Continuous Improvement:

Review Frequency: Monthly

Improvement Inputs:

Feedback from stakeholders

#### Pre-PI Planning – Identify Features

Description:

The Product Management team identifies potential features that align with the refined program vision and key themes. This involves brainstorming sessions, reviewing customer feedback, and analyzing market trends to generate a comprehensive list of potential features. The team also considers any technical constraints or dependencies that may impact the feasibility of each feature.

Responsible Party:

Product Management

Inputs:

Refined program vision

Key themes and objectives

Outputs:

List of potential features

Feature descriptions

Estimated Duration:

3 days

Dependencies:

Refine Program Vision

Success Criteria:

Comprehensive list of potential features is generated

Feature descriptions are created

Purpose:

To generate a comprehensive list of potential features.

Scope:

Identification of potential features and creation of descriptions.

Process Owner:

Product Manager

Triggers:

Refined program vision completed

Key themes and objectives completed

End Conditions:

List of potential features completed

Feature descriptions completed

Step Risks and Controls:

Risk: Missing key features

Control: Regular brainstorming sessions with stakeholders

Governance Requirements:

Stakeholder review of potential features

Change Management:

Change Request Process: Formal change request

Versioning Rules: Document versioning

Continuous Improvement:

Review Frequency: Monthly

Improvement Inputs:

Feedback from stakeholders

#### Pre-PI Planning – Prioritize Features

Description:

The Product Management team prioritizes the identified features based on their alignment with the program vision, business value, and technical feasibility. This involves using a prioritization framework such as Weighted Shortest Job First (WSJF) or MoSCoW to rank the features and determine which ones should be included in the upcoming PI. The team also considers any dependencies or constraints that may impact the prioritization process.

Responsible Party:

Product Management

Inputs:

List of potential features

Feature descriptions

Outputs:

Prioritized feature list

Feature ranking

Estimated Duration:

2 days

Dependencies:

Identify Features

Success Criteria:

Features are prioritized based on business value and technical feasibility

Feature ranking is completed

Purpose:

To prioritize features based on business value and technical feasibility.

Scope:

Prioritization of features and creation of ranking.

Process Owner:

Product Manager

Triggers:

List of potential features completed

Feature descriptions completed

End Conditions:

Prioritized feature list completed

Feature ranking completed

Step Risks and Controls:

Risk: Incorrect prioritization of features

Control: Regular review of prioritization with stakeholders

Governance Requirements:

Stakeholder review of prioritized feature list

Change Management:

Change Request Process: Formal change request

Versioning Rules: Document versioning

Continuous Improvement:

Review Frequency: Monthly

Improvement Inputs:

Feedback from stakeholders

#### Pre-PI Planning – Define Acceptance Criteria

Description:

For each prioritized feature, the Product Management team defines clear and measurable acceptance criteria to ensure that the feature meets the desired requirements. This involves collaborating with stakeholders to define the specific conditions that must be met for the feature to be considered complete. The team also considers any potential risks or dependencies that may impact the acceptance criteria.

Responsible Party:

Product Management

Inputs:

Prioritized feature list

Feature ranking

Outputs:

Acceptance criteria for each feature

Feature acceptance tests

Estimated Duration:

3 days

Dependencies:

Prioritize Features

Success Criteria:

Acceptance criteria are clearly defined for each feature

Feature acceptance tests are created

Purpose:

To define clear and measurable acceptance criteria for each feature.

Scope:

Definition of acceptance criteria and creation of acceptance tests.

Process Owner:

Product Manager

Triggers:

Prioritized feature list completed

Feature ranking completed

End Conditions:

Acceptance criteria for each feature completed

Feature acceptance tests completed

Step Risks and Controls:

Risk: Unclear acceptance criteria

Control: Regular review of acceptance criteria with stakeholders

Governance Requirements:

Stakeholder review of acceptance criteria

Change Management:

Change Request Process: Formal change request

Versioning Rules: Document versioning

Continuous Improvement:

Review Frequency: Monthly

Improvement Inputs:

Feedback from stakeholders

#### Pre-PI Planning – Estimate Feature Effort

Description:

The Development Teams estimate the effort required to develop and test each feature. This involves using estimation techniques such as story points or t-shirt sizing to assign a relative size to each feature. The team also considers any technical complexities or dependencies that may impact the estimation process. The System Architect provides guidance on architectural runway and technical feasibility.

Responsible Party:

Development Teams

Inputs:

Acceptance criteria for each feature

Feature acceptance tests

Outputs:

Effort estimates for each feature

Feature story points

Estimated Duration:

2 days

Dependencies:

Define Acceptance Criteria

Success Criteria:

Effort estimates are completed for each feature

Feature story points are assigned

Purpose:

To estimate the effort required to develop and test each feature.

Scope:

Estimation of feature effort and assignment of story points.

Process Owner:

Development Team

Triggers:

Acceptance criteria for each feature completed

Feature acceptance tests completed

End Conditions:

Effort estimates for each feature completed

Feature story points completed

Step Risks and Controls:

Risk: Inaccurate effort estimates

Control: Regular review of estimates with development teams

Governance Requirements:

Development Team review of effort estimates

Change Management:

Change Request Process: Iteration change request

Versioning Rules: Version control system

Continuous Improvement:

Review Frequency: Sprint retrospective

Improvement Inputs:

Team feedback

#### Pre-PI Planning – Refine Program Backlog

Description:

The Product Management team refines the program backlog based on the prioritized features, acceptance criteria, and effort estimates. This involves creating user stories for each feature, adding them to the program backlog, and ensuring that they are properly tagged and categorized. The team also identifies any dependencies or constraints that may impact the program backlog.

Responsible Party:

Product Management

Inputs:

Effort estimates for each feature

Feature story points

Outputs:

Refined program backlog

User stories for each feature

Estimated Duration:

2 days

Dependencies:

Estimate Feature Effort

Success Criteria:

Program backlog is refined with user stories

User stories are properly tagged and categorized

Purpose:

To refine the program backlog with user stories.

Scope:

Refinement of program backlog and creation of user stories.

Process Owner:

Product Manager

Triggers:

Effort estimates for each feature completed

Feature story points completed

End Conditions:

Refined program backlog completed

User stories for each feature completed

Step Risks and Controls:

Risk: Incomplete program backlog

Control: Regular review of program backlog with stakeholders

Governance Requirements:

Stakeholder review of program backlog

Change Management:

Change Request Process: Formal change request

Versioning Rules: Document versioning

Continuous Improvement:

Review Frequency: Monthly

Improvement Inputs:

Feedback from stakeholders

#### Pre-PI Planning – Prepare PI Planning Inputs

Description:

The Product Management team prepares the inputs for the upcoming PI Planning session. This involves creating a draft PI plan, identifying any potential risks or dependencies, and communicating the program vision and key themes to the Agile Release Train (ART). The team also ensures that all necessary documentation and resources are available for the PI Planning session.

Responsible Party:

Product Management

Inputs:

Refined program backlog

User stories for each feature

Outputs:

Draft PI plan

PI Planning inputs

Estimated Duration:

1 day

Dependencies:

Refine Program Backlog

Success Criteria:

Draft PI plan is created

PI Planning inputs are prepared

Purpose:

To prepare the inputs for the upcoming PI Planning session.

Scope:

Preparation of PI Planning inputs and creation of draft PI plan.

Process Owner:

Product Manager

Triggers:

Refined program backlog completed

User stories for each feature completed

End Conditions:

Draft PI plan completed

PI Planning inputs completed

Step Risks and Controls:

Risk: Inadequate PI Planning inputs

Control: Regular review of PI Planning inputs with stakeholders

Governance Requirements:

Stakeholder review of PI Planning inputs

Change Management:

Change Request Process: Formal change request

Versioning Rules: Document versioning

Continuous Improvement:

Review Frequency: Monthly

Improvement Inputs:

Feedback from stakeholders

## 3.2 PI Planning

Description:

PI Planning is a big room planning event where all teams within the Agile Release Train (ART) come together to align on a common mission and plan the upcoming Program Increment (PI). During this event, teams review the program backlog, identify dependencies, and commit to PI Objectives. The outputs of this step include a set of PI Objectives and team iteration plans that provide a roadmap for the upcoming PI.

Responsible Parties:

Release Train Engineer (RTE)

Success Criteria:

Teams commit to PI Objectives and dependencies are identified.

### Required Sub Process(es) for the Step "PI Planning"

The following details the subprocess flows for the step "PI Planning".

#### PI Planning – Prepare PI Planning Logistics

Description:

The Release Train Engineer (RTE) is responsible for coordinating and preparing the logistics for the PI Planning event. This includes scheduling the event, booking the venue, arranging for necessary equipment (projectors, whiteboards, collaboration tools), and communicating the event details to all participants. Ensuring smooth logistics is crucial for a productive and efficient PI Planning session.

Responsible Party:

Release Train Engineer (RTE)

Inputs:

Outputs:

PI Planning schedule

Venue booking confirmation

Equipment checklist

Communication to participants

Estimated Duration:

1 week

Dependencies:

Success Criteria:

PI Planning event is scheduled and confirmed

Venue is booked and equipped

Participants are informed of event details

Purpose:

Ensure all logistical aspects of PI Planning are in place for a smooth event.

Scope:

Program level

Process Owner:

Release Train Engineer (RTE)

Triggers:

Scheduled PI Planning event

End Conditions:

Logistics are confirmed and communicated

Step Risks and Controls:

Risk: Venue unavailability

Control: Book venue well in advance and have backup options

Governance Requirements:

Change Management:

Change Request Process: Changes to logistics require RTE approval

Versioning Rules: Track changes to schedule and venue

Continuous Improvement:

Review Frequency: Post-PI Planning

Improvement Inputs:

Team feedback on logistics

#### PI Planning – Review Program Backlog

Description:

Product Management reviews the program backlog with key stakeholders to ensure it is prioritized and reflects the current business needs. This involves refining user stories, defining acceptance criteria, and estimating story points. A well-groomed backlog ensures that teams have clear and actionable items to plan during PI Planning.

Responsible Party:

Product Management

Inputs:

Business strategy

Market analysis

Customer feedback

Outputs:

Prioritized program backlog

Refined user stories

Estimated Duration:

2 days

Dependencies:

Prepare PI Planning Logistics

Success Criteria:

Program backlog is prioritized and refined

User stories have clear acceptance criteria

Story points are estimated

Purpose:

Ensure the program backlog is ready for teams to plan their iterations.

Scope:

Program level

Process Owner:

Product Management

Triggers:

Scheduled PI Planning event

End Conditions:

Program backlog is reviewed and prioritized

Step Risks and Controls:

Risk: Misaligned priorities

Control: Regular backlog refinement sessions with stakeholders

Governance Requirements:

Stakeholder review of backlog

Change Management:

Change Request Process: Changes to backlog require Product Management approval

Versioning Rules: Track changes to user stories and priorities

Continuous Improvement:

Review Frequency: Post-PI Planning

Improvement Inputs:

Team feedback on backlog clarity

#### PI Planning – Present Business Context and Vision

Description:

Business Owners and Product Management present the current business context, strategic vision, and top priorities to the Agile Release Train (ART). This provides teams with the necessary information to make informed decisions during planning. A clear understanding of the business context is essential for aligning team efforts with overall business goals.

Responsible Party:

Business Owners, Product Management

Inputs:

Prioritized program backlog

Business strategy

Market analysis

Outputs:

Business context presentation

Vision document

Estimated Duration:

2–4 hours

Dependencies:

Review Program Backlog

Success Criteria:

Business context and vision are clearly communicated

Teams understand top priorities

Purpose:

Provide teams with the necessary context to align their planning with business goals.

Scope:

Program level

Process Owner:

Product Management

Triggers:

Start of PI Planning event

End Conditions:

Business context and vision are presented

Step Risks and Controls:

Risk: Misunderstanding of business goals

Control: Interactive Q&A session after presentation

Governance Requirements:

Change Management:

Change Request Process: Changes to vision require Business Owner approval

Versioning Rules: Track changes to vision document

Continuous Improvement:

Review Frequency: Post-PI Planning

Improvement Inputs:

Team feedback on presentation clarity

#### PI Planning – Team Breakout Sessions

Description:

Teams break out to plan their individual iterations for the upcoming Program Increment (PI). This involves selecting user stories from the program backlog, identifying dependencies, and estimating the work required. Effective team breakout sessions are crucial for creating realistic and achievable iteration plans.

Responsible Party:

Development Teams

Inputs:

Business context presentation

Vision document

Prioritized program backlog

Outputs:

Team iteration plans

Identified dependencies

Estimated Duration:

1 day

Dependencies:

Present Business Context and Vision

Success Criteria:

Teams create realistic iteration plans

Dependencies are identified and documented

Purpose:

Enable teams to create detailed plans for their iterations within the PI.

Scope:

Team level

Process Owner:

Development Team

Triggers:

After business context presentation

End Conditions:

Team iteration plans are created

Step Risks and Controls:

Risk: Unrealistic commitments

Control: Capacity planning and risk assessment

Governance Requirements:

Change Management:

Change Request Process: Changes to iteration plans require team agreement

Versioning Rules: Track changes to iteration plans

Continuous Improvement:

Review Frequency: Post-PI Planning

Improvement Inputs:

Team feedback on planning process

#### PI Planning – Draft Plan Review

Description:

Each team presents their draft iteration plans to the rest of the Agile Release Train (ART) for review and feedback. This allows teams to identify potential dependencies and conflicts early in the planning process. Constructive feedback during the draft plan review is essential for ensuring a cohesive and aligned PI plan.

Responsible Party:

Development Teams

Inputs:

Team iteration plans

Identified dependencies

Outputs:

Feedback on iteration plans

Identified dependencies and conflicts

Estimated Duration:

2–4 hours

Dependencies:

Team Breakout Sessions

Success Criteria:

Teams present their draft plans

Feedback is provided and documented

Dependencies and conflicts are identified

Purpose:

Identify dependencies and conflicts early in the planning process.

Scope:

Program level

Process Owner:

Release Train Engineer (RTE)

Triggers:

After team breakout sessions

End Conditions:

Draft plans are reviewed and feedback is provided

Step Risks and Controls:

Risk: Lack of participation

Control: Encourage active participation from all teams

Governance Requirements:

Change Management:

Change Request Process: Changes to plans based on feedback require team agreement

Versioning Rules: Track changes to plans based on feedback

Continuous Improvement:

Review Frequency: Post-PI Planning

Improvement Inputs:

Team feedback on review process

#### PI Planning – Final Plan Adjustments

Description:

Teams adjust their iteration plans based on the feedback received during the draft plan review. This involves resolving dependencies, addressing conflicts, and ensuring that the plans are realistic and achievable. Making necessary adjustments is crucial for creating a final PI plan that is aligned and executable.

Responsible Party:

Development Teams

Inputs:

Feedback on iteration plans

Identified dependencies and conflicts

Team iteration plans

Outputs:

Adjusted team iteration plans

Estimated Duration:

2–4 hours

Dependencies:

Draft Plan Review

Success Criteria:

Iteration plans are adjusted based on feedback

Dependencies and conflicts are resolved

Purpose:

Create a final PI plan that is aligned and executable.

Scope:

Team level

Process Owner:

Development Team

Triggers:

After draft plan review

End Conditions:

Iteration plans are adjusted

Step Risks and Controls:

Risk: Incomplete resolution of dependencies

Control: Facilitate dependency resolution workshops

Governance Requirements:

Change Management:

Change Request Process: Changes to plans require team agreement

Versioning Rules: Track changes to plans

Continuous Improvement:

Review Frequency: Post-PI Planning

Improvement Inputs:

Team feedback on adjustment process

#### PI Planning – Commitment and Confidence Vote

Description:

Teams commit to their final iteration plans and provide a confidence vote indicating their level of confidence in achieving the PI Objectives. This provides a transparent view of the ART's overall commitment and identifies potential risks. A high level of commitment and confidence is essential for a successful PI.

Responsible Party:

Development Teams

Inputs:

Adjusted team iteration plans

Outputs:

Committed iteration plans

Confidence vote results

Estimated Duration:

1 hour

Dependencies:

Final Plan Adjustments

Success Criteria:

Teams commit to their plans

Confidence vote is conducted

Purpose:

Provide a transparent view of the ART's overall commitment and identify potential risks.

Scope:

Program level

Process Owner:

Release Train Engineer (RTE)

Triggers:

After final plan adjustments

End Conditions:

Teams commit to plans and confidence vote is conducted

Step Risks and Controls:

Risk: Low confidence

Control: Address concerns and adjust plans as needed

Governance Requirements:

Change Management:

Change Request Process: Changes after commitment require RTE approval

Versioning Rules: Track changes to plans after commitment

Continuous Improvement:

Review Frequency: Post-PI Planning

Improvement Inputs:

Team feedback on commitment process

#### PI Planning – Create Program Board

Description:

The Release Train Engineer (RTE) creates a program board that visualizes the PI Objectives, dependencies, and risks for the upcoming Program Increment (PI). This provides a clear and transparent view of the overall plan and facilitates communication across teams. A well-maintained program board is crucial for tracking progress and managing dependencies throughout the PI.

Responsible Party:

Release Train Engineer (RTE)

Inputs:

Committed iteration plans

Confidence vote results

Identified dependencies

Outputs:

Program board

Estimated Duration:

2–4 hours

Dependencies:

Commitment and Confidence Vote

Success Criteria:

Program board is created and visualized

PI Objectives, dependencies, and risks are clearly displayed

Purpose:

Visualize the PI plan and facilitate communication across teams.

Scope:

Program level

Process Owner:

Release Train Engineer (RTE)

Triggers:

After commitment and confidence vote

End Conditions:

Program board is created

Step Risks and Controls:

Risk: Inaccurate representation of dependencies

Control: Validate dependencies with teams

Governance Requirements:

Change Management:

Change Request Process: Changes to program board require RTE approval

Versioning Rules: Track changes to program board

Continuous Improvement:

Review Frequency: Post-PI Planning

Improvement Inputs:

Team feedback on program board clarity

## 3.3 Iteration Execution

Description:

During Iteration Execution, development teams build and test features based on the iteration plans created during PI Planning. This involves writing code, conducting unit tests, integrating code changes, and performing system testing. The outputs of this step include working software and tested features that are ready for integration and demonstration.

Responsible Parties:

Development Teams

Success Criteria:

Features are developed, tested, and integrated.

### Required Sub Process(es) for the Step "Iteration Execution"

The following details the subprocess flows for the step "Iteration Execution".

#### Iteration Execution – Code Development

Description:

Development teams begin writing code based on the user stories and tasks defined in the iteration plan. This involves adhering to coding standards, utilizing appropriate design patterns, and implementing the necessary functionality to meet the acceptance criteria. Developers work collaboratively, often using pair programming or code reviews, to ensure code quality and knowledge sharing.

Responsible Party:

Development Teams

Inputs:

Iteration Plan

User Stories

Acceptance Criteria

Outputs:

Source Code

Code Documentation

Estimated Duration:

3-5 days

Dependencies:

Success Criteria:

Code meets acceptance criteria

Code adheres to coding standards

Code is documented

Purpose:

To implement the features and functionalities defined in the iteration plan.

Scope:

Team level

Process Owner:

Development Team

Triggers:

Start of iteration

End Conditions:

Code development complete for all tasks

Step Risks and Controls:

Risk: Code defects

Control: Code reviews and unit testing

Risk: Misinterpretation of requirements

Control: Daily stand-ups and clarification with product owner

Governance Requirements:

Coding standards compliance

Code review sign-off

Change Management:

Change Request Process: Iteration change request

Versioning Rules: Version control system

Continuous Improvement:

Review Frequency: Sprint retrospective

Improvement Inputs:

Team feedback

Code quality metrics

#### Iteration Execution – Unit Testing

Description:

Developers create and execute unit tests to verify the correctness of individual components and functions. This involves writing test cases that cover various scenarios, including positive and negative cases, boundary conditions, and error handling. Unit tests are automated and integrated into the CI/CD pipeline to ensure continuous feedback on code quality.

Responsible Party:

Development Teams

Inputs:

Source Code

Test Cases

Outputs:

Unit Test Results

Code Coverage Metrics

Estimated Duration:

1-2 days

Dependencies:

Code Development

Success Criteria:

Unit tests pass

Code coverage meets defined threshold

No critical defects found

Purpose:

To ensure the correctness and reliability of individual code components.

Scope:

Team level

Process Owner:

Development Team

Triggers:

Code development complete for a component

End Conditions:

Unit testing complete for all components

Step Risks and Controls:

Risk: Insufficient test coverage

Control: Code coverage analysis and test case review

Risk: Flaky tests

Control: Test isolation and retry mechanisms

Governance Requirements:

Test case documentation

Code coverage reporting

Change Management:

Change Request Process: Iteration change request

Versioning Rules: Version control system

Continuous Improvement:

Review Frequency: Sprint retrospective

Improvement Inputs:

Team feedback

Test execution metrics

#### Iteration Execution – Code Integration

Description:

Integrated code changes into the shared repository. This involves resolving conflicts, merging code branches, and ensuring that the integrated code builds successfully. Continuous integration practices are followed to automate the integration process and provide rapid feedback on integration issues. The System Team may be involved to assist with environment provisioning and build automation.

Responsible Party:

Development Teams

Inputs:

Source Code

Unit Test Results

Outputs:

Integrated Codebase

Build Status

Estimated Duration:

1 day

Dependencies:

Unit Testing

Success Criteria:

Code integrates without conflicts

Build is successful

All unit tests pass after integration

Purpose:

To combine code changes from multiple developers into a single, working codebase.

Scope:

Team level

Process Owner:

Development Team

Triggers:

Completion of unit testing

End Conditions:

Code integration complete and build is successful

Step Risks and Controls:

Risk: Integration conflicts

Control: Frequent integration and automated conflict resolution tools

Risk: Build failures

Control: Automated build verification and rollback mechanisms

Governance Requirements:

Build automation compliance

Version control system compliance

Change Management:

Change Request Process: Iteration change request

Versioning Rules: Version control system

Continuous Improvement:

Review Frequency: Sprint retrospective

Improvement Inputs:

Team feedback

Build success rate

#### Iteration Execution – System Testing

Description:

The integrated codebase is subjected to system testing to verify that the system as a whole meets the defined requirements and acceptance criteria. This involves executing test cases that cover various aspects of the system, including functionality, performance, security, and usability. The System Team often assists with setting up the test environment and providing test automation support.

Responsible Party:

Development Teams

Inputs:

Integrated Codebase

Test Cases

Acceptance Criteria

Outputs:

System Test Results

Defect Reports

Estimated Duration:

2-3 days

Dependencies:

Code Integration

Success Criteria:

System meets acceptance criteria

No critical defects found

Performance meets defined thresholds

Purpose:

To validate that the integrated system meets the defined requirements and acceptance criteria.

Scope:

Team level

Process Owner:

Development Team

Triggers:

Successful code integration

End Conditions:

System testing complete and all critical defects resolved

Step Risks and Controls:

Risk: System defects

Control: Thorough test case design and execution

Risk: Performance bottlenecks

Control: Performance testing and optimization

Governance Requirements:

Test execution reporting

Defect tracking and resolution

Change Management:

Change Request Process: Iteration change request

Versioning Rules: Version control system

Continuous Improvement:

Review Frequency: Sprint retrospective

Improvement Inputs:

Team feedback

Defect density

## 3.4 System Demos

Description:

System Demos are conducted at the end of each iteration to showcase the integrated system functionality to stakeholders. This provides an opportunity to gather feedback, identify potential issues, and ensure that the system is meeting the needs of its users. The outputs of this step include a working system demo and feedback from stakeholders that can be used to improve the system.

Responsible Parties:

System Team

Inputs:

Iteration Review Feedback

Test Results

Feature Documentation

Success Criteria:

Integrated system functionality is demonstrated to stakeholders.

### Required Sub Process(es) for the Step "System Demos"

The following details the subprocess flows for the step "System Demos".

#### System Demos – Prepare Demo Environment

Description:

The System Team prepares the demo environment by ensuring all necessary components are correctly configured and running. This includes deploying the latest build, configuring necessary data, and verifying network connectivity. A stable and representative environment is crucial for a successful demo.

Responsible Party:

System Team

Inputs:

Test Results

Feature Documentation

Deployment Scripts

Outputs:

Prepared Demo Environment

Environment Configuration Documentation

Estimated Duration:

4-8 hours

Dependencies:

Success Criteria:

Environment is stable and representative

All components are correctly configured

Network connectivity is verified

Purpose:

To ensure a stable and representative environment for the system demo.

Scope:

Program level

Process Owner:

System Team

Triggers:

End of iteration

Notification of upcoming demo

End Conditions:

Demo environment is fully configured and tested

Step Risks and Controls:

Risk: Environment instability

Control: Automated deployment and configuration scripts

Governance Requirements:

Environment configuration documentation

Change management approval for environment changes

Change Management:

Change Request Process: Standard change management process

Versioning Rules: Version control for environment configuration scripts

Continuous Improvement:

Review Frequency: Post-demo

Improvement Inputs:

Demo feedback

Environment performance metrics

#### System Demos – Develop Demo Script

Description:

The System Team develops a demo script that showcases the integrated system functionality and highlights key features. This script should be concise, engaging, and tailored to the interests of the stakeholders. The script should also include contingency plans for potential issues that may arise during the demo.

Responsible Party:

System Team

Inputs:

Feature Documentation

Iteration Review Feedback

Stakeholder Profiles

Outputs:

Demo Script

Contingency Plans

Estimated Duration:

2-4 hours

Dependencies:

Success Criteria:

Demo script is concise and engaging

Key features are highlighted

Contingency plans are in place

Purpose:

To create a structured and engaging presentation of the system functionality.

Scope:

Program level

Process Owner:

System Team

Triggers:

End of iteration

Feature completion

End Conditions:

Demo script is finalized and approved

Step Risks and Controls:

Risk: Demo script is not engaging

Control: Review and feedback from stakeholders

Governance Requirements:

Stakeholder approval of demo script

Change Management:

Change Request Process: Demo script change request process

Versioning Rules: Version control for demo script

Continuous Improvement:

Review Frequency: Post-demo

Improvement Inputs:

Stakeholder feedback

Demo effectiveness metrics

#### System Demos – Conduct Dry Runs

Description:

The System Team conducts dry runs of the demo to identify and resolve any potential issues. This includes practicing the demo script, verifying environment stability, and testing contingency plans. Dry runs are essential for ensuring a smooth and professional demo.

Responsible Party:

System Team

Inputs:

Demo Script

Prepared Demo Environment

Outputs:

Identified Issues

Revised Demo Script

Environment Fixes

Estimated Duration:

2-4 hours

Dependencies:

Prepare Demo Environment

Develop Demo Script

Success Criteria:

Demo runs smoothly without issues

Environment is stable during the demo

Contingency plans are tested and effective

Purpose:

To identify and resolve any potential issues before the actual demo.

Scope:

Program level

Process Owner:

System Team

Triggers:

Completion of demo script

Availability of demo environment

End Conditions:

Dry runs are completed and all issues are resolved

Step Risks and Controls:

Risk: Unidentified issues during the demo

Control: Multiple dry runs with different team members

Governance Requirements:

Documentation of dry run results

Change Management:

Change Request Process: Demo script change request process

Versioning Rules: Version control for demo script

Continuous Improvement:

Review Frequency: Post-demo

Improvement Inputs:

Dry run results

Team feedback

#### System Demos – Present System Demo

Description:

The System Team presents the system demo to stakeholders, showcasing the integrated system functionality and highlighting key features. This includes following the demo script, engaging with the audience, and addressing any questions or concerns. A professional and engaging presentation is crucial for gathering valuable feedback.

Responsible Party:

System Team

Inputs:

Demo Script

Prepared Demo Environment

Outputs:

Stakeholder Feedback

Identified Issues

Estimated Duration:

1-2 hours

Dependencies:

Conduct Dry Runs

Success Criteria:

Integrated system functionality is demonstrated

Stakeholders are engaged and provide feedback

Questions and concerns are addressed

Purpose:

To showcase the integrated system functionality and gather feedback from stakeholders.

Scope:

Program level

Process Owner:

System Team

Triggers:

End of iteration

Scheduled demo time

End Conditions:

Demo is completed and stakeholder feedback is received

Step Risks and Controls:

Risk: Technical issues during the demo

Control: Backup environment and contingency plans

Governance Requirements:

Stakeholder attendance and feedback

Change Management:

Change Request Process: Demo feedback process

Versioning Rules: Track feedback and changes

Continuous Improvement:

Review Frequency: Post-demo

Improvement Inputs:

Stakeholder feedback

Demo effectiveness metrics

#### System Demos – Gather Stakeholder Feedback

Description:

The System Team actively gathers feedback from stakeholders following the system demo. This includes soliciting feedback on the system functionality, user interface, and overall value. Gathering comprehensive feedback is crucial for identifying areas for improvement and ensuring that the system meets the needs of its users.

Responsible Party:

System Team

Inputs:

System Demo

Stakeholder Attendance

Outputs:

Compiled Stakeholder Feedback

Feedback Summary Report

Estimated Duration:

30 minutes - 1 hour

Dependencies:

Present System Demo

Success Criteria:

Feedback is gathered from all key stakeholders

Feedback is comprehensive and addresses key areas

Feedback is documented and summarized

Purpose:

To collect comprehensive feedback from stakeholders to identify areas for improvement.

Scope:

Program level

Process Owner:

System Team

Triggers:

Completion of system demo

End Conditions:

Stakeholder feedback is compiled and summarized

Step Risks and Controls:

Risk: Incomplete or biased feedback

Control: Structured feedback forms and follow-up interviews

Governance Requirements:

Documentation of stakeholder feedback

Change Management:

Change Request Process: Demo feedback process

Versioning Rules: Track feedback and changes

Continuous Improvement:

Review Frequency: Post-demo

Improvement Inputs:

Stakeholder feedback

Feedback analysis

#### System Demos – Analyze Feedback and Identify Improvements

Description:

The System Team analyzes the stakeholder feedback to identify potential issues and areas for improvement. This includes categorizing feedback, prioritizing issues, and developing action plans. Analyzing feedback and identifying improvements is crucial for ensuring that the system continuously evolves to meet the needs of its users.

Responsible Party:

System Team

Inputs:

Compiled Stakeholder Feedback

Test Results

Outputs:

Prioritized Issues List

Action Plans

Updated Backlog Items

Estimated Duration:

2-4 hours

Dependencies:

Gather Stakeholder Feedback

Success Criteria:

Feedback is categorized and prioritized

Action plans are developed for key issues

Backlog items are updated to reflect feedback

Purpose:

To analyze stakeholder feedback and identify actionable improvements for the system.

Scope:

Program level

Process Owner:

System Team

Triggers:

Completion of feedback gathering

End Conditions:

Feedback is analyzed, and action plans are developed

Step Risks and Controls:

Risk: Misinterpretation of feedback

Control: Cross-validation with stakeholders and product owners

Governance Requirements:

Documentation of feedback analysis and action plans

Change Management:

Change Request Process: Standard change management process

Versioning Rules: Track changes to backlog items

Continuous Improvement:

Review Frequency: Post-demo

Improvement Inputs:

Action plan effectiveness

Stakeholder satisfaction

## 3.5 Release

Description:

The Release step involves deploying features to production, making them available to end-users. This includes packaging the software, deploying it to the production environment, and conducting post-deployment testing to ensure that everything is working as expected. The outputs of this step include deployed features and release notes that document the changes made in the release.

Responsible Parties:

Deployment Management, Release Train Engineer, System Architect

Success Criteria:

Features are successfully deployed to production.

### Required Sub Process(es) for the Step "Release"

The following details the subprocess flows for the step "Release".

#### Release – Prepare Release Package

Description:

The first step in the release process is to prepare the release package. This involves gathering all the necessary components, including the software binaries, configuration files, and any supporting documentation. The package is then versioned and tagged for easy identification and tracking. This ensures that all components are properly assembled and ready for deployment.

Responsible Party:

Deployment Management

Inputs:

Software binaries

Configuration files

Release notes

Supporting documentation

Outputs:

Versioned release package

Estimated Duration:

1 day

Dependencies:

Success Criteria:

Release package is complete and versioned

Purpose:

Assemble all necessary components into a deployable package.

Scope:

Packaging of software and related artifacts.

Process Owner:

Deployment Management

Triggers:

Release candidate ready

End Conditions:

Release package created

Step Risks and Controls:

Risk: Incomplete release package

Control: Checklist and verification process

Governance Requirements:

Version control

Change management approval

Change Management:

Change Request Process: Release change request

Versioning Rules: Release versioning

Continuous Improvement:

Review Frequency: Post-release

Improvement Inputs:

Deployment feedback

#### Release – Deploy to Staging Environment

Description:

Before deploying to production, the release package is deployed to a staging environment. This environment closely mirrors the production environment and is used to perform final testing and validation. This step helps to identify any potential issues or conflicts before they impact the live system. The deployment process is automated to ensure consistency and reduce the risk of human error.

Responsible Party:

System Team

Inputs:

Versioned release package

Outputs:

Deployed features in staging environment

Estimated Duration:

2 days

Dependencies:

Prepare Release Package

Success Criteria:

Successful deployment to staging environment

Purpose:

Validate the release package in a production-like environment.

Scope:

Deployment and configuration in staging.

Process Owner:

System Team

Triggers:

Release package created

End Conditions:

Staging deployment complete

Step Risks and Controls:

Risk: Deployment failure in staging

Control: Automated deployment scripts and rollback plan

Governance Requirements:

Environment validation

Security review

Change Management:

Change Request Process: Release change request

Versioning Rules: Release versioning

Continuous Improvement:

Review Frequency: Post-release

Improvement Inputs:

Deployment feedback

#### Release – Conduct Post-Deployment Testing

Description:

Once the release package is deployed to the staging environment, a series of post-deployment tests are conducted. These tests include functional testing, performance testing, and security testing to ensure that the system is working as expected and that there are no vulnerabilities. The System Architect and Development Teams collaborate to validate the deployed features and ensure they meet the defined success criteria.

Responsible Party:

Development Teams, System Architect

Inputs:

Deployed features in staging environment

Outputs:

Test results

Validation report

Estimated Duration:

2 days

Dependencies:

Deploy to Staging Environment

Success Criteria:

All tests pass successfully

Validation report approved

Purpose:

Ensure the deployed features function correctly and meet quality standards.

Scope:

Testing and validation in staging.

Process Owner:

Development Teams

Triggers:

Staging deployment complete

End Conditions:

Testing complete and validation report approved

Step Risks and Controls:

Risk: Defects found in staging

Control: Defect tracking and resolution process

Governance Requirements:

Test coverage

Defect tracking

Change Management:

Change Request Process: Release change request

Versioning Rules: Release versioning

Continuous Improvement:

Review Frequency: Post-release

Improvement Inputs:

Test results

#### Release – Obtain Final Approval

Description:

After successful testing in the staging environment, final approval is obtained from the process owner and relevant stakeholders. This approval confirms that the release is ready for deployment to production. The Release Train Engineer (RTE) ensures that all governance requirements have been met and that all stakeholders are aligned on the release plan.

Responsible Party:

Release Train Engineer (RTE), Process Owner

Inputs:

Validation report

Outputs:

Final approval

Estimated Duration:

1 day

Dependencies:

Conduct Post-Deployment Testing

Success Criteria:

Final approval obtained from all stakeholders

Purpose:

Secure stakeholder agreement before production deployment.

Scope:

Stakeholder sign-off and governance.

Process Owner:

Release Train Engineer (RTE)

Triggers:

Testing complete and validation report approved

End Conditions:

Final approval received

Step Risks and Controls:

Risk: Release not approved

Control: Clear communication and escalation process

Governance Requirements:

Stakeholder sign-off

Compliance review

Change Management:

Change Request Process: Release change request

Versioning Rules: Release versioning

Continuous Improvement:

Review Frequency: Post-release

Improvement Inputs:

Stakeholder feedback

#### Release – Deploy to Production Environment

Description:

With final approval in hand, the release package is deployed to the production environment. This deployment is carefully monitored to ensure that everything goes smoothly. The Deployment Management team uses automated deployment tools to minimize downtime and ensure consistency. The System Architect oversees the deployment to ensure architectural integrity and stability.

Responsible Party:

Deployment Management, System Architect

Inputs:

Final approval

Versioned release package

Outputs:

Deployed features in production

Estimated Duration:

4 hours

Dependencies:

Obtain Final Approval

Success Criteria:

Successful deployment to production environment

Purpose:

Make the new features available to end-users.

Scope:

Deployment and configuration in production.

Process Owner:

Deployment Management

Triggers:

Final approval received

End Conditions:

Production deployment complete

Step Risks and Controls:

Risk: Deployment failure in production

Control: Automated deployment scripts and rollback plan

Governance Requirements:

Change management approval

Security compliance

Change Management:

Change Request Process: Release change request

Versioning Rules: Release versioning

Continuous Improvement:

Review Frequency: Post-release

Improvement Inputs:

Deployment feedback

#### Release – Conduct Post-Release Monitoring

Description:

After the deployment to production, the system is closely monitored to ensure that everything is working as expected. This includes monitoring system performance, error logs, and user feedback. The System Team and Development Teams collaborate to quickly address any issues that arise. This monitoring continues for a defined period to ensure stability and performance.

Responsible Party:

System Team, Development Teams

Inputs:

Deployed features in production

Outputs:

Monitoring reports

Error logs

User feedback

Estimated Duration:

3 days

Dependencies:

Deploy to Production Environment

Success Criteria:

System performance is stable

No critical errors reported

Purpose:

Ensure the deployed features are stable and perform as expected in production.

Scope:

Monitoring and issue resolution in production.

Process Owner:

System Team

Triggers:

Production deployment complete

End Conditions:

Monitoring period complete and system stable

Step Risks and Controls:

Risk: System instability

Control: Automated monitoring tools and incident response plan

Governance Requirements:

Performance monitoring

Incident management

Change Management:

Change Request Process: Release change request

Versioning Rules: Release versioning

Continuous Improvement:

Review Frequency: Post-release

Improvement Inputs:

Monitoring reports

User feedback

#### Release – Document Release

Description:

Finally, the release is documented, including any changes made, issues encountered, and resolutions implemented. This documentation is stored in a central repository for future reference. The Release Notes are updated to reflect the final state of the release, and any lessons learned are captured for continuous improvement. This ensures that the organization has a clear record of the release process and can learn from past experiences.

Responsible Party:

Deployment Management

Inputs:

Monitoring reports

Error logs

User feedback

Outputs:

Updated release notes

Release documentation

Estimated Duration:

4 hours

Dependencies:

Conduct Post-Release Monitoring

Success Criteria:

Release documentation is complete and accurate

Purpose:

Maintain a record of the release for future reference and continuous improvement.

Scope:

Documentation and archiving of release information.

Process Owner:

Deployment Management

Triggers:

Monitoring period complete and system stable

End Conditions:

Release documentation complete

Step Risks and Controls:

Risk: Incomplete documentation

Control: Documentation checklist and review process

Governance Requirements:

Documentation standards

Archival policy

Change Management:

Change Request Process: Release change request

Versioning Rules: Release versioning

Continuous Improvement:

Review Frequency: Post-release

Improvement Inputs:

Documentation feedback

## 3.6 Inspect and Adapt

Description:

The Inspect and Adapt (I&A) event is a significant event, held at the end of each PI, where the current state of the solution is demonstrated and evaluated by the teams. Teams then identify improvement items via a structured, problem-solving workshop. The outputs of this step include an improvement plan and action items that are incorporated into the next PI Planning session to drive continuous improvement.

Responsible Parties:

Release Train Engineer (RTE)

Success Criteria:

Identified process improvements and action items.

### Required Sub Process(es) for the Step "Inspect and Adapt"

The following details the subprocess flows for the step "Inspect and Adapt".

#### Inspect and Adapt – Prepare for I&A Workshop

Description:

The Release Train Engineer (RTE) schedules the Inspect and Adapt (I&A) workshop, ensuring all relevant stakeholders are invited, including representatives from each team, product management, system architects, and business owners. The RTE also prepares the agenda, ensuring it covers the demonstration of the current solution, data review, problem-solving workshop, and identification of improvement items. Finally, the RTE ensures the necessary tools and materials are available, such as collaboration platforms, whiteboards, and data reports.

Responsible Party:

Release Train Engineer (RTE)

Inputs:

Outputs:

I&A Workshop agenda

List of attendees

Required tools and materials

Estimated Duration:

2 hours

Dependencies:

Success Criteria:

Workshop scheduled with all stakeholders

Agenda prepared and communicated

Tools and materials ready

Purpose:

To ensure the I&A workshop is well-organized and productive.

Scope:

Program level

Process Owner:

Release Train Engineer (RTE)

Triggers:

End of PI

End Conditions:

Workshop agenda finalized

Attendees confirmed

Materials prepared

Step Risks and Controls:

Risk: Poor attendance

Control: Send reminders and emphasize the importance of the workshop

Governance Requirements:

Stakeholder attendance

Change Management:

Change Request Process: Email to RTE

Versioning Rules: Track changes to agenda

Continuous Improvement:

Review Frequency: Post-workshop

Improvement Inputs:

Attendee feedback

#### Inspect and Adapt – Solution Demo

Description:

The System Team, along with representatives from the development teams, demonstrates the current state of the solution to all stakeholders. This demonstration should cover all key features and functionalities delivered during the PI, highlighting any significant achievements or challenges encountered. The demonstration should be interactive, allowing stakeholders to ask questions and provide feedback on the solution's performance and usability. The System Architect provides context on architectural decisions.

Responsible Party:

System Team

Inputs:

Outputs:

Working system demo

Stakeholder feedback

Estimated Duration:

2 hours

Dependencies:

Prepare for I&A Workshop

Success Criteria:

All key features demonstrated

Stakeholder feedback collected

Purpose:

To provide stakeholders with a clear understanding of the current state of the solution.

Scope:

Program level

Process Owner:

System Team

Triggers:

Start of I&A Workshop

End Conditions:

Solution demo completed

Feedback documented

Step Risks and Controls:

Risk: Demo failure

Control: Prepare backup plans and dry runs

Governance Requirements:

Stakeholder attendance and feedback

Change Management:

Change Request Process: Verbal feedback during demo

Versioning Rules: Track feedback and changes

Continuous Improvement:

Review Frequency: Post-demo

Improvement Inputs:

Stakeholder feedback

#### Inspect and Adapt – Data Review

Description:

The RTE presents data related to the PI's performance, including metrics such as program predictability, team velocity, defect density, and release frequency. This data should be presented in a clear and concise manner, highlighting any trends or areas of concern. The RTE facilitates a discussion around the data, encouraging stakeholders to share their insights and perspectives on the PI's performance. The RTE also presents data on dependencies and risks encountered during the PI.

Responsible Party:

Release Train Engineer (RTE)

Inputs:

Outputs:

PI performance data

Stakeholder insights

Estimated Duration:

1 hour

Dependencies:

Solution Demo

Success Criteria:

PI performance data presented

Stakeholder insights documented

Purpose:

To provide stakeholders with a data-driven understanding of the PI's performance.

Scope:

Program level

Process Owner:

Release Train Engineer (RTE)

Triggers:

Completion of Solution Demo

End Conditions:

Data review completed

Insights documented

Step Risks and Controls:

Risk: Data misinterpretation

Control: Provide clear explanations and context

Governance Requirements:

Data accuracy

Change Management:

Change Request Process: Email to RTE

Versioning Rules: Track changes to data presentation

Continuous Improvement:

Review Frequency: Post-workshop

Improvement Inputs:

Stakeholder feedback

#### Inspect and Adapt – Problem-Solving Workshop

Description:

Facilitated by the RTE, stakeholders participate in a structured problem-solving workshop to identify the root causes of any issues or challenges encountered during the PI. This workshop should follow a defined process, such as the 5 Whys or Fishbone diagram, to ensure a thorough analysis. The workshop should be collaborative, encouraging all stakeholders to contribute their ideas and perspectives. The System Architect provides technical insights.

Responsible Party:

Release Train Engineer (RTE)

Inputs:

Outputs:

Identified root causes

Potential solutions

Estimated Duration:

3 hours

Dependencies:

Data Review

Success Criteria:

Root causes identified

Potential solutions generated

Purpose:

To identify the root causes of issues and generate potential solutions.

Scope:

Program level

Process Owner:

Release Train Engineer (RTE)

Triggers:

Completion of Data Review

End Conditions:

Problem-solving workshop completed

Root causes and solutions documented

Step Risks and Controls:

Risk: Lack of participation

Control: Encourage active participation and create a safe environment

Governance Requirements:

Action item tracking

Change Management:

Change Request Process: Verbal feedback during workshop

Versioning Rules: Track feedback and changes

Continuous Improvement:

Review Frequency: Post-workshop

Improvement Inputs:

Attendee feedback

#### Inspect and Adapt – Identify Improvement Items

Description:

Based on the identified root causes and potential solutions, stakeholders identify specific improvement items that can be implemented in the next PI. These improvement items should be actionable, measurable, achievable, relevant, and time-bound (SMART). The improvement items should be prioritized based on their potential impact and feasibility. The RTE ensures that the improvement items are documented and assigned to responsible parties.

Responsible Party:

Release Train Engineer (RTE)

Inputs:

Identified root causes

Potential solutions

Outputs:

Prioritized improvement items

Assigned responsible parties

Estimated Duration:

2 hours

Dependencies:

Problem-Solving Workshop

Success Criteria:

SMART improvement items identified

Improvement items prioritized

Responsible parties assigned

Purpose:

To identify and prioritize actionable improvement items for the next PI.

Scope:

Program level

Process Owner:

Release Train Engineer (RTE)

Triggers:

Completion of Problem-Solving Workshop

End Conditions:

Improvement items documented

Priorities set

Assignments made

Step Risks and Controls:

Risk: Unrealistic improvement items

Control: Ensure improvement items are SMART

Governance Requirements:

Action item tracking

Change Management:

Change Request Process: Email to RTE

Versioning Rules: Track changes to improvement items

Continuous Improvement:

Review Frequency: Post-PI

Improvement Inputs:

Team feedback

#### Inspect and Adapt – Create Improvement Plan

Description:

The RTE compiles all identified improvement items into a comprehensive improvement plan. This plan should include a description of each improvement item, the responsible party, the expected benefits, and the timeline for implementation. The improvement plan should be communicated to all stakeholders and incorporated into the next PI Planning session. The RTE tracks the progress of the improvement plan and reports on its effectiveness.

Responsible Party:

Release Train Engineer (RTE)

Inputs:

Prioritized improvement items

Assigned responsible parties

Outputs:

Improvement plan

Estimated Duration:

2 hours

Dependencies:

Identify Improvement Items

Success Criteria:

Improvement plan created

Plan communicated to stakeholders

Purpose:

To create a roadmap for implementing the identified improvement items.

Scope:

Program level

Process Owner:

Release Train Engineer (RTE)

Triggers:

Completion of Improvement Item Identification

End Conditions:

Improvement plan finalized

Plan communicated

Step Risks and Controls:

Risk: Lack of implementation

Control: Track progress and report on effectiveness

Governance Requirements:

Action item tracking

Change Management:

Change Request Process: Email to RTE

Versioning Rules: Track changes to improvement plan

Continuous Improvement:

Review Frequency: Ongoing

Improvement Inputs:

Team feedback

## 3.7 Innovation and Planning (IP) Iteration

Description:

The Innovation and Planning (IP) Iteration provides dedicated time for innovation, learning, and PI Planning preparation. During this iteration, teams can explore new technologies, experiment with new ideas, and prepare for the upcoming PI Planning session. The outputs of this step include innovation prototypes, learning summaries, and PI Planning inputs that can be used to drive innovation and improve the overall SDLC process.

Responsible Parties:

Development Teams

Success Criteria:

Innovation prototypes and PI Planning inputs are created.

### Required Sub Process(es) for the Step "Innovation and Planning (IP) Iteration"

The following details the subprocess flows for the step "Innovation and Planning (IP) Iteration".

#### Innovation and Planning (IP) Iteration – Technology Exploration

Description:

Development teams dedicate time to explore new technologies relevant to the program's architectural runway and future product capabilities. This involves researching emerging trends, evaluating potential tools and frameworks, and conducting proof-of-concept experiments to assess their feasibility and value. The goal is to identify technologies that can enhance the program's ability to deliver innovative solutions and improve its overall technical agility.

Responsible Party:

Development Teams

Inputs:

Outputs:

Technology evaluation reports

Proof-of-concept prototypes

Estimated Duration:

3 days

Dependencies:

Success Criteria:

Relevant new technologies are identified and evaluated.

Proof-of-concept prototypes demonstrate the feasibility of selected technologies.

Purpose:

Identify and evaluate new technologies for potential adoption within the program.

Scope:

Team level

Process Owner:

Development Teams

Triggers:

Scheduled IP Iteration

End Conditions:

Technology evaluation reports and proof-of-concept prototypes are completed.

Step Risks and Controls:

Risk: Selection of inappropriate technologies

Control: Conduct thorough evaluations and involve system architects in the decision-making process.

Governance Requirements:

Change Management:

Change Request Process: Innovation request

Versioning Rules: Track technology changes

Continuous Improvement:

Review Frequency: Post-IP Iteration

Improvement Inputs:

Team feedback

Technology performance data

#### Innovation and Planning (IP) Iteration – Experimentation and Prototyping

Description:

Teams engage in experimentation and prototyping to explore new ideas and validate potential solutions. This involves creating rapid prototypes, conducting user testing, and gathering feedback to iterate on designs and refine concepts. The focus is on fostering a culture of experimentation and learning, where teams are empowered to take risks and explore unconventional approaches to problem-solving.

Responsible Party:

Development Teams

Inputs:

Technology evaluation reports

Outputs:

Innovation prototypes

User feedback summaries

Estimated Duration:

5 days

Dependencies:

Technology Exploration

Success Criteria:

Innovation prototypes are created and tested with users.

User feedback is gathered and incorporated into prototype designs.

Purpose:

Explore new ideas and validate potential solutions through experimentation and prototyping.

Scope:

Team level

Process Owner:

Development Teams

Triggers:

Scheduled IP Iteration

End Conditions:

Innovation prototypes are tested and user feedback is summarized.

Step Risks and Controls:

Risk: Wasting time on unpromising ideas

Control: Establish clear criteria for evaluating ideas and conduct regular reviews to assess progress.

Governance Requirements:

Change Management:

Change Request Process: Innovation request

Versioning Rules: Track prototype changes

Continuous Improvement:

Review Frequency: Post-IP Iteration

Improvement Inputs:

Team feedback

User feedback summaries

#### Innovation and Planning (IP) Iteration – Learning and Knowledge Sharing

Description:

Teams document their learning and share their knowledge with the broader organization. This involves creating learning summaries, conducting presentations, and participating in knowledge-sharing sessions. The goal is to disseminate insights gained during the IP Iteration and promote a culture of continuous learning and improvement across the program.

Responsible Party:

Development Teams

Inputs:

User feedback summaries

Innovation prototypes

Outputs:

Learning summaries

Presentation materials

Estimated Duration:

2 days

Dependencies:

Experimentation and Prototyping

Success Criteria:

Learning summaries are created and shared with the organization.

Presentations are conducted to disseminate insights gained during the IP Iteration.

Purpose:

Disseminate insights gained during the IP Iteration and promote a culture of continuous learning.

Scope:

Team level

Process Owner:

Development Teams

Triggers:

Scheduled IP Iteration

End Conditions:

Learning summaries and presentation materials are completed.

Step Risks and Controls:

Risk: Knowledge is not effectively shared

Control: Establish clear guidelines for documenting learning and provide incentives for knowledge sharing.

Governance Requirements:

Innovation showcase

Change Management:

Change Request Process: Innovation request

Versioning Rules: Track learning changes

Continuous Improvement:

Review Frequency: Post-IP Iteration

Improvement Inputs:

Team feedback

Feedback from knowledge-sharing sessions

#### Innovation and Planning (IP) Iteration – PI Planning Preparation

Description:

Teams prepare for the upcoming PI Planning session by reviewing the program backlog, identifying dependencies, and estimating the effort required for each feature. This involves collaborating with product management and other stakeholders to refine the backlog and ensure that it is aligned with strategic objectives. The goal is to ensure that the PI Planning session is productive and efficient, and that teams are able to commit to realistic PI Objectives.

Responsible Party:

Development Teams

Inputs:

Learning summaries

Program backlog

Outputs:

PI Planning inputs

Estimated Duration:

4 days

Dependencies:

Learning and Knowledge Sharing

Success Criteria:

PI Planning inputs are created and shared with stakeholders.

Teams are prepared to commit to realistic PI Objectives.

Purpose:

Prepare for the upcoming PI Planning session and ensure that teams are able to commit to realistic PI Objectives.

Scope:

Team level

Process Owner:

Development Teams

Triggers:

Scheduled IP Iteration

End Conditions:

PI Planning inputs are completed.

Step Risks and Controls:

Risk: Inadequate preparation for PI Planning

Control: Establish clear guidelines for PI Planning preparation and provide teams with the necessary resources and support.

Governance Requirements:

Change Management:

Change Request Process: Innovation request

Versioning Rules: Track PI Planning input changes

Continuous Improvement:

Review Frequency: Post-IP Iteration

Improvement Inputs:

Team feedback

Feedback from PI Planning session

# 4.0 Supporting Systems and Tools

The following tools and platforms support this process:

| Category | Tools |
| --- | --- |
| Agile Project Management | Jira, Azure DevOps |
| CI/CD | Jenkins, GitLab CI |
| Collaboration | Slack, Microsoft Teams |
| Testing Automation | Selenium, JUnit |
| Version Control | Git |
| Security Scanning | SonarQube, Fortify |

# 5.0 Metrics and Key Performance Indicators (KPIs)

The following is a list of key metrics associated with this process. These metrics help monitor performance and ensure alignment with business objectives.

| Metric | Description | Measurement / Frequency | Target |
| --- | --- | --- | --- |
| Program Predictability Measure | Measures the predictability of delivering PI Objectives. | Per PI | 80% |
| Team Velocity | Measures the rate at which teams deliver value, providing insights into team performance and identifying potential bottlenecks. | Per iteration | Consistent velocity |
| Defect Density | Measures the number of defects per line of code, providing an indication of code quality and the effectiveness of testing efforts. | Per release | <1 defect/1000 LOC |
| Release Frequency | Measures the frequency of releases to production, indicating the organization's ability to deliver value to customers quickly and reliably. | Monthly | Monthly releases |
| Customer Satisfaction | Measures customer satisfaction with delivered features, providing valuable feedback for continuous improvement and ensuring that the organization is meeting customer needs. | Post-release | 4.5/5 rating |

# 6.0 Critical Success Factors (CSF)

The following is a list of key CSFs associated with this process.

| Success Factor | Description |
| --- | --- |
| Effective PI Planning | Effective PI Planning ensures alignment and commitment across teams, leading to more predictable and successful outcomes. |
| Strong RTE leadership | Strong RTE leadership facilitates program execution, removes impediments, and ensures that teams are working towards common goals. |
| Cross-functional collaboration | Cross-functional collaboration ensures smooth communication and collaboration across teams, leading to more efficient and effective development. |
| Continuous Integration/Continuous Delivery (CI/CD) | Continuous Integration/Continuous Delivery (CI/CD) enables frequent and reliable releases, allowing organizations to deliver value to customers more quickly. |
| Alignment with business goals | Alignment with business goals ensures that development efforts are aligned with business objectives, leading to more valuable and impactful outcomes. |

# 7.0 Critical Failure Factors (CFF)

The following is a list of key CFFs associated with this process.

| Failure Factor | Description |
| --- | --- |
| Poor communication | Poor communication between teams and stakeholders can lead to misunderstandings, delays, and ultimately, project failure. |
| Lack of stakeholder engagement | A lack of stakeholder engagement can result in misaligned priorities and unmet expectations, leading to dissatisfaction and project failure. |
| Unrealistic expectations | Setting unrealistic expectations can cause frustration and burnout among team members, negatively impacting morale and productivity. |
| Technical debt | Accumulating technical debt can slow down development, increase maintenance costs, and make it more difficult to implement new features. |
| Inadequate testing | Inadequate testing can result in defects, customer dissatisfaction, and ultimately, damage to the organization's reputation. |

# 8.0 Reporting and Analytics

The following are key reporting and analytics associated with this process.

| Description | Metric |
| --- | --- |
| Provides an overview of program progress and risks, enabling stakeholders to make informed decisions and take corrective actions as needed. | Program progress reports |
| Tracks the progress of releases, providing insights into the organization's ability to deliver value to customers on a regular basis. | Release burndown charts |
| Measures team velocity and identifies bottlenecks, enabling teams to improve their performance and optimize their workflows. | Team velocity reports |
| Tracks the number and severity of defects, providing an indication of code quality and the effectiveness of testing efforts. | Defect tracking reports |
| Identifies bottlenecks and inefficiencies in the value stream, enabling organizations to streamline their processes and improve their overall efficiency. | Value stream mapping |

# 9.0 System Requirements

The following system requirements are essential for the successful implementation of this process.

| Details | Name |
| --- | --- |
| Used for managing the program and team backlogs, tracking progress, and facilitating collaboration. | Agile project management software (e.g., Jira, Azure DevOps) |
| Used for automating the build, test, and deployment processes. | CI/CD pipeline (e.g., Jenkins, GitLab CI) |
| Used for facilitating communication and collaboration across teams. | Collaboration tools (e.g., Slack, Microsoft Teams) |
| Used for automating the testing process and ensuring code quality. | Testing automation tools |
| Used for managing source code and tracking changes. | Version control system (e.g., Git) |
| Used for identifying security vulnerabilities and ensuring code security. | Security scanning tools (e.g., SonarQube, Fortify) |

# 10.0 Process Flow Diagram

The following diagram provides a high-level visualization of the process flow as defined in the normalized JSON source.

# 11.0 Process Performance Report

The following metrics are based on a Monte Carlo discrete-event simulation running 2,000 iterations. All time-based values are reported in weeks.

| Operational Metric | Simulated Value |
| --- | --- |
| Average Cycle Time | 12.10 weeks |
| Cycle Time Variance | 1.20 weeks |
| Contention Risk Profile | Low |

## Identified Bottlenecks

Pre-PI Planning

PI Planning

Iteration Execution

## Detailed Step Performance

| Process Step | Avg. Duration (weeks) |
| --- | --- |
| Pre-PI Planning | 2.70 |
| PI Planning | 2.69 |
| Iteration Execution | 2.69 |
| System Demos | 1.35 |
| Release | 1.34 |
| Inspect and Adapt | 1.33 |
| Innovation and Planning (IP) Iteration | 2.67 |

# 12.0 Governance Requirements

There following are the list of governance requirements used in this process.

Regular audits of SAFe implementation

Compliance with industry standards

Stakeholder reviews of program progress

# 13.0 Risks and Controls

The following risks and associated controls apply to this process.

| Risk | Control |
| --- | --- |
| Dependency conflicts | Dependency mapping and proactive communication |
| Scope creep | Strict change management process and backlog prioritization |
| Technical debt | Dedicated time for refactoring and technical improvements |

# 14.0 Process Triggers

There following are triggers that kick processes off.

New feature request

Business opportunity

Market change

Regulatory requirement

# 15.0 Process End Conditions

There following are a list of the process end conditions.

Feature deployed to production

Value delivered to customer

Release objectives met

# 16.0 Change Management

There following are list of the change management procedures.

Change Request Process: Formal change request process

Versioning Rules: Document versioning control

# 17.0 Continuous Improvement

The following are the items used for continuous improvement.

Review Frequency: Regularly

Improvement Inputs:

Regular retrospectives

Value stream mapping

Kaizen workshops

Feedback loops with stakeholders

# Appendix B: Additional Source Data

This appendix contains additional structured data from the normalized source JSON that is not covered in the main sections.

Purpose: This process aims to provide a structured framework for developing and delivering software products at the enterprise level, aligning with strategic business goals and delivering value to stakeholders through Agile and SAFe methodologies. It ensures that software development efforts are aligned with business objectives by prioritizing features that directly contribute to key performance indicators (KPIs) such as increased revenue, reduced costs, or improved customer satisfaction. For example, a key performance indicator (KPI) directly impacted by this process could be a reduction in time-to-market for new features, an increase in customer satisfaction scores, or a decrease in development costs. The process promotes collaboration and communication across teams through standardized processes and regular synchronization meetings, and enables the delivery of high-quality software products in a timely and efficient manner by leveraging continuous integration and continuous delivery (CI/CD) practices.

Process Owner: Program Manager/Release Train Engineer

Scope: This process encompasses all software development activities from initial planning and requirements gathering to production deployment and ongoing maintenance. It includes program management, release train coordination, team-level execution, and applies to large-scale enterprise projects that require cross-team coordination and alignment with strategic business goals. For example, this process would be used for developing a new e-commerce platform, migrating a legacy system to the cloud, or building a new customer relationship management (CRM) platform. This process excludes small, isolated projects that do not require significant cross-team coordination or alignment with enterprise-level objectives, such as developing a simple mobile app, creating a single landing page, or developing a proof-of-concept application.

# Appendix C: Glossary

This glossary contains definitions of common terms used in the process documentation.

| Term | Definition |
| --- | --- |
| Business Process | A set of related activities or tasks performed to achieve a specific organizational goal. |
| KPI | Key Performance Indicator used to measure the success or health of a process. |
| Stakeholder | Any individual or group with an interest in the outcomes of the process. |
| Continuous Improvement | Ongoing effort to improve products, services or processes. |